## EXCEL
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assigned To | Status
1 | Define Job Requirements | 2024-02-05 | 2024-02-13 | 8 | HR Manager | Completed
2 | Post Job Advertisement | 2024-02-08 | 2024-02-10 | 3 | HR Team | Completed
3 | Resume Screening | 2024-02-11 | 2024-02-28 | 17 | HR Team | In Progress
4 | Initial Phone Interview | 2024-02-15 | 2024-02-18 | 4 | HR Executive | Pending
5 | Technical Test | 2024-02-01 | 2024-02-01 | 0 | Tech Lead | Pending
6 | First Round Interview | 2024-02-20 | 2024-02-26 | 6 | Hiring Manager | Pending
7 | Final Interview | 2024-02-21 | 2024-02-29 | 8 | Director | Pending
8 | Offer Letter & Negotiation | 2024-03-01 | 2024-03-12 | 11 | HR Manager | Pending
9 | Onboarding Process | 2024-03-04 | 2024-03-14 | 10 | HR Team | Pending